## Sheet1
ID | US | BV | Priority | Effort
8 | As a Supervisor, I want to log visits manually so that I can record visit details when a QR code is unavailable. | High | 1 | 5
9 | As a Supervisor, I want to log visits using a QR code scanner so that I can quickly and accurately record visit details. | High | 2 | 8
10 | As a Supervisor, I want to validate checklists for each visit so that all required tasks are completed. | High | 3 | 5
16 | As a Supervisor, I want to create new timesheets so that I can manage my weekly schedule. | High | 4 | 5
21 | As a Manager, I want to view and validate timesheets so that accuracy is maintained. | High | 5 | 5
22 | As a Manager, I want to generate dynamic reports filtered by date range so that specific periods can be analyzed. | High | 6 | 8
27 | As a Manager, I want to view KPI dashboards with charts and graphs so that key performance indicators can be visualized. | High | 7 | 8
32 | As an AI Model, I want to analyze timesheet and visit data to detect irregularities so that potential issues can be flagged. | High | 8 | 8
1 | As a User, I want to securely log in using my credentials so that I can access the platform. | Medium | 9 | 3
3 | As an Admin, I want to create new user accounts so that users can access the platform. | Medium | 10 | 5
6 | As an Admin, I want to assign roles to users so that they have appropriate permissions. | Medium | 11 | 5
18 | As a Supervisor, I want to receive real-time notifications for visits so that I know what to do. | Medium | 12 | 5
19 | As a Supervisor, I want to use a responsive mobile application so that I can access the platform conveniently. | Medium | 13 | 13
20 | As a Supervisor, I want to enter data offline so that I can continue working without internet connectivity. | Medium | 14 | 8
23 | As a Manager, I want to generate dynamic reports filtered by supervisor so that individual performance can be assessed. | Medium | 15 | 5
24 | As a Manager, I want to generate dynamic reports filtered by region so that regional performance can be evaluated. | Medium | 16 | 5
25 | As a Manager, I want to export reports in PDF format so that they can be shared easily. | Medium | 17 | 3
26 | As a Manager, I want to export reports in Excel format so that further analysis can be performed. | Medium | 18 | 3
28 | As a Manager, I want to receive anomaly alerts in dashboards so that issues can be addressed promptly. | Medium | 19 | 5
29 | As a Manager, I want to receive real-time notifications for pending validations so that I can take necessary actions. | Medium | 20 | 5
30 | As a Manager, I want to receive real-time notifications for detected anomalies so that timely interventions can occur. | Medium | 21 | 5
33 | As an AI Model, I want to generate automated reports using predictive analytics so that comprehensive insights can be provided. | Medium | 22 | 8
34 | As an AI Model, I want to send real-time alerts based on findings so that relevant users can act immediately. | Medium | 23 | 5
2 | As a User, I want to edit my own profile information so that my details are accurate. | Low | 24 | 2
4 | As an Admin, I want to modify existing user accounts so that user information remains up-to-date. | Low | 25 | 3
5 | As an Admin, I want to delete user accounts so that inactive or unnecessary accounts can be removed. | Low | 26 | 3
7 | As an Admin, I want to revoke roles from users so that permissions can be adjusted as needed. | Low | 27 | 3
11 | As a Supervisor, I want to upload photos related to the visit so that visual documentation is available. | Low | 28 | 3
12 | As a Supervisor, I want to add comments to visit logs so that additional context can be provided. | Low | 29 | 2
13 | As a Supervisor, I want to view past visit logs so that I can review historical data. | Low | 30 | 3
14 | As a Supervisor, I want to edit past visit logs so that corrections can be made. | Low | 31 | 3
15 | As a Supervisor, I want to delete visit logs so that incorrect entries can be removed. | Low | 32 | 2
17 | As a Supervisor, I want to update existing timesheets so that changes can be reflected. | Low | 33 | 3
31 | As an HR, I want to review timesheets so that employee attendance and performance can be monitored. | Low | 34 | 3