## Sheet2
ID | US | BV | Priority | Effort
8 | As a Supervisor, I want to log visits manually so that I can record visit details when a QR code is unavailable. | High | 1 | 5
9 | As a Supervisor, I want to log visits using a QR code scanner so that I can quickly and accurately record visit details. | High | 2 | 8
10 | As a Supervisor, I want to validate checklists for each visit so that all required tasks are completed. | High | 3 | 5
16 | As a Supervisor, I want to create new timesheets so that I can manage my weekly schedule. | High | 4 | 5
21 | As a Manager, I want to view and validate timesheets so that accuracy is maintained. | High | 5 | 5
22 | As a Manager, I want to generate dynamic reports filtered by date range so that specific periods can be analyzed. | High | 6 | 8
27 | As a Manager, I want to view KPI dashboards with charts and graphs so that key performance indicators can be visualized. | High | 7 | 8
32 | As an AI Model, I want to analyze timesheet and visit data to detect irregularities so that potential issues can be flagged. | High | 8 | 8
1 | As a User, I want to securely log in using my credentials so that I can access the platform. | Medium | 9 | 3
3 | As an Admin, I want to create new user accounts so that users can access the platform. | Medium | 10 | 5
6 | As an Admin, I want to assign roles to users so that they have appropriate permissions. | Medium | 11 | 5
18 | As a Supervisor, I want to receive real-time notifications for visits so that I know what to do. | Medium | 12 | 5
19 | As a Supervisor, I want to use a responsive mobile application so that I can access the platform conveniently. | Medium | 13 | 13
20 | As a Supervisor, I want to enter data offline so that I can continue working without internet connectivity. | Medium | 14 | 8
23 | As a Manager, I want to generate dynamic reports filtered by supervisor so that individual performance can be assessed. | Medium | 15 | 5
24 | As a Manager, I want to generate dynamic reports filtered by region so that regional performance can be evaluated. | Medium | 16 | 5
25 | As a Manager, I want to export reports in PDF format so that they can be shared easily. | Medium | 17 | 3
26 | As a Manager, I want to export reports in Excel format so that further analysis can be performed. | Medium | 18 | 3
28 | As a Manager, I want to receive anomaly alerts in dashboards so that issues can be addressed promptly. | Medium | 19 | 5
29 | As a Manager, I want to receive real-time notifications for pending validations so that I can take necessary actions. | Medium | 20 | 5
30 | As a Manager, I want to receive real-time notifications for detected anomalies so that timely interventions can occur. | Medium | 21 | 5
33 | As an AI Model, I want to generate automated reports using predictive analytics so that comprehensive insights can be provided. | Medium | 22 | 8
34 | As an AI Model, I want to send real-time alerts based on findings so that relevant users can act immediately. | Medium | 23 | 5
2 | As a User, I want to edit my own profile information so that my details are accurate. | Low | 24 | 2
4 | As an Admin, I want to modify existing user accounts so that user information remains up-to-date. | Low | 25 | 3
5 | As an Admin, I want to delete user accounts so that inactive or unnecessary accounts can be removed. | Low | 26 | 3
7 | As an Admin, I want to revoke roles from users so that permissions can be adjusted as needed. | Low | 27 | 3
11 | As a Supervisor, I want to upload photos related to the visit so that visual documentation is available. | Low | 28 | 3
12 | As a Supervisor, I want to add comments to visit logs so that additional context can be provided. | Low | 29 | 2
13 | As a Supervisor, I want to view past visit logs so that I can review historical data. | Low | 30 | 3
14 | As a Supervisor, I want to edit past visit logs so that corrections can be made. | Low | 31 | 3
15 | As a Supervisor, I want to delete visit logs so that incorrect entries can be removed. | Low | 32 | 2
17 | As a Supervisor, I want to update existing timesheets so that changes can be reflected. | Low | 33 | 3
31 | As an HR, I want to review timesheets so that employee attendance and performance can be monitored. | Low | 34 | 3

## P
User Story | Description | BV | Priority | Effort
As an HR I want to receive alerts for anomalies so that issues are addressed promptly. | HR Anomaly Alerts | Medium | 29 | 3
As an HR I want to monitor timesheets globally so that attendance is tracked. | Global Timesheet Monitoring | Medium | 18 | 5
As an HR I want to monitor global activity through dashboards so that trends are visible. | Global Activity Monitoring | Medium | 17 | 5
As an Admin I want to oversee all timesheets so that there is full transparency. | Timesheet Oversight | Medium | 23 | 5
As an Admin I want to edit user profiles so that user details remain up-to-date. | Profile Editing | Medium | 24 | 3
As an Admin I want to delete user accounts so that inactive users are removed. | Account Deletion | Medium | 25 | 3
As an Admin I want to create user accounts so that users can access the platform securely. | Account Creation | High | 15 | 5
As an Admin I want Phi-4 to ensure data integrity so that anomalies are minimized. | Data Integrity | Medium | 22 | 8
As a User I want to update my profile so that my personal information is accurate. | Profile Update | Low | 32 | 2
As a User I want to reset my password so that I can regain access if forgotten. | Password Reset | Medium | 27 | 3
As a User I want to receive real-time notifications so that I stay informed. | Real-Time Notifications | Medium | 28 | 8
As a User I want to log in securely so that my data is protected. | Secure Login | Medium | 26 | 5
As a Supervisor I want to view/edit past visit logs so that I can correct errors. | Edit Past Visits | Medium | 12 | 5
As a Supervisor I want to validate checklists during visits so that compliance is ensured. | Checklist Validation | High | 2 | 8
As a Supervisor I want to upload photos during visits so that visual evidence is recorded. | Photo Uploads | Medium | 3 | 5
As a Supervisor I want to log visits via QR code scanning so that the process is faster. | QR Code Logging | Medium | 11 | 8
As a Supervisor I want to log visits manually so that I can record details of agent interactions. | Manual Visit Logging | High | 1 | 8
As a Supervisor I want to delete visit logs so that irrelevant entries are removed. | Log Deletion | Low | 31 | 3
As a Supervisor I want to create and update timesheets so that my work hours are tracked. | Timesheet Management | High | 4 | 8
As a Supervisor I want to confirm visit notifications so that my actions are acknowledged. | Visit Confirmations | Medium | 16 | 5
As a Supervisor I want offline capabilities in the mobile app so that data is saved locally. | Offline Capabilities | Medium | 10 | 13
As a Supervisor I want a mobile app to log visits so that I can work on the go. | Mobile Visit Logging | Medium | 9 | 13
As a Manager I want to view KPI dashboards so that I can track progress visually. | KPI Dashboards | High | 6 | 8
As a Manager I want to review and validate timesheets so that accuracy is ensured. | Timesheet Validation | High | 5 | 5
As a Manager I want to receive alerts for pending validations so that processes are not delayed. | Pending Validation Alerts | Medium | 19 | 5
As a Manager I want to receive alerts for anomalies so that issues are addressed promptly. | Anomaly Alerts | Medium | 30 | 8
As a Manager I want to generate dynamic reports so that I can analyze performance. | Dynamic Report Generation | High | 8 | 13
As a Manager I want to filter reports by date, region or supervisor so that insights are precise. | Report Filtering | High | 7 | 8
As a Manager I want to export reports in PDF/Excel so that they can be shared externally. | Report Export | Medium | 13 | 5
As a Manager I want Phi-4 to predict trends so that proactive decisions can be made. | Trend Prediction | Medium | 21 | 8
As a Manager I want Phi-4 to generate automated reports so that manual effort is reduced. | Automated Reporting | High | 14 | 13
As a Manager I want Phi-4 to detect anomalies in timesheets so that irregularities are flagged. | Anomaly Detection | Medium | 20 | 13

## P1
Week | Phase | Detailed Tasks | Deliverables
1 | Sprint 1: Project Planning & System Design | 🔹 Define Scope & Product Backlog: Identify features & tasks | ✅ Product Backlog Document
|  | 🔹 UML Diagrams: Create Use Case Diagram, System Overview, Initial Class Diagram, High-Level Data Flow (DFD) | ✅ UML: Use Case, System Overview, DFD, Class Diagram
|  | 🔹 Setup Development Environment: Install Node.js, PostgreSQL, Flutter, TensorFlow.js (Phi-4), GitHub repo setup | ✅ GitHub Repository Setup
🔹 Plan AI Model Integration: Research Phi-4 capabilities & define AI use cases
2 | Sprint 1 (Continued): Authentication & Role Management | 🔹 User Roles & Permissions: Define Admin, HR, Manager, Supervisor | ✅ Functional Login & Registration System
|  | 🔹 Develop Authentication System: JWT-based login/logout & role-based access control (RBAC) | ✅ RBAC Implemented & Tested
|  | 🔹 Database Schema: PostgreSQL schema for users & permissions | ✅ API Documentation (Auth)
🔹 Testing: Unit tests for authentication (Jest, Mocha)
🔹 Documentation: API reference for authentication
3 | Sprint 2: Visit Logging & Timesheet Management (Backend) | 🔹 Develop Visit Logging API: CRUD endpoints for visit logs | ✅ Backend APIs for Visits & Timesheets
|  | 🔹 Develop Timesheet API: CRUD endpoints for time tracking | ✅ PostgreSQL Schema Ready
🔹 Database Schema: Tables for visits & timesheets
🔹 Backend Validation: Implement input validation for data consistency
🔹 Testing: API Integration Tests (Postman, Jest)
4 | Sprint 2 (Continued): Visit Logging & Timesheet UI (Web & Mobile) | 🔹 Develop Web Dashboard (React.js): UI for logging visits & managing timesheets | ✅ Functional Visit & Timesheet UI
|  | 🔹 Develop Mobile App (Flutter): UI for visit logging | ✅ QR Code Scanning Feature Implemented
🔹 QR Code Scanning Feature: Implement QR-based check-in
🔹 Real-Time Updates: Use Socket.IO for real-time changes
🔹 Testing: Frontend & mobile UI validation
5 | Sprint 3: Reporting & Dashboard Development | 🔹 Generate Reports: Dynamic filters (date, region, agent) | ✅ Dashboard with KPI Metrics
|  | 🔹 Export Data: Enable PDF & Excel report export | ✅ Export Feature (PDF, Excel)
🔹 Charts & Graphs: KPI Visualization (Visit stats, timesheets)
🔹 Testing: Report accuracy validation
6 | Sprint 3 (Continued): Notifications & Alerts | 🔹 Implement Real-Time Alerts: Web & Mobile notifications for anomalies, approvals | ✅ Real-Time Notifications Functional
|  | 🔹 Push Notifications: Flutter (FCM) & Web (Socket.IO) | ✅ Push Alerts Integrated
🔹 Testing: Notification accuracy & speed
🔹 UML Diagrams: Sequence Diagram for Notifications
7 | Sprint 4: AI Integration - Phi-4 Anomaly Detection (Backend) | 🔹 Fine-Tune Phi-4 for Anomaly Detection: Customize detection for irregular visit logs & timesheets | ✅ Phi-4 AI Integrated
|  | 🔹 Integrate AI with Backend: Develop endpoints to query AI model | ✅ AI-Powered Anomaly Detection Working
🔹 Database Connection: Store AI-generated insights
🔹 Testing: Validate AI predictions with real data
8 | Sprint 4 (Continued): AI Visualization in UI | 🔹 UI for AI Alerts: Display detected anomalies | ✅ AI Alerts Visible in Dashboard
🔹 Interactive Filtering: Allow managers to sort alerts
🔹 Testing: AI alert effectiveness & real-time updates
9-10 | Sprint 5: Performance Optimization & Security Hardening | 🔹 Optimize Database Queries: Use indexing, caching | ✅ Optimized API & Database Performance
|  | 🔹 Enhance API Speed: Optimize response times | ✅ Security Audits Completed
🔹 Implement Security Features: Encrypt data, secure endpoints, OAuth for API access
🔹 Penetration Testing: Check for vulnerabilities
11-12 | Sprint 6: Full System Testing | 🔹 Automated Testing: Cypress for end-to-end tests | ✅ Fully Tested System (Unit, Integration, Load)
🔹 Load Testing: Simulate 1000+ concurrent users
🔹 Bug Fixing: Address critical issues before deployment
13-14 | Sprint 7: Documentation & Training | 🔹 Technical Documentation: API references, UML Diagrams | ✅ Comprehensive Documentation Ready
🔹 User Manuals: Step-by-step guides for end users
🔹 Training Materials: Video tutorials (if needed)
15-16 | Sprint 8: Deployment & Finalization | 🔹 Deploy Backend & Database: Server configuration | ✅ Live System + Final Presentation 🎉
🔹 Deploy Mobile App: Publish on Google Play & App Store
🔹 Final Testing in Production
🔹 Create Final Presentation & Report

## P2
📌 Sprint 1: Project Planning & System Design (Week 1-2)
Goal: Define requirements, backlog, UML diagrams, environment setup, and release plan.
Day | Tasks | Deliverables
Day 1 (Monday) | 📌 Read and analyze project study (Cahier des Charges) | ✅ Key Functionalities List
📌 Identify key functionalities
Day 2 (Tuesday) | 📌 Define functional requirements (visits, timesheets, reporting, notifications, AI integration) | ✅ Functional & Non-Functional Requirements Document
📌 Define non-functional requirements (security, performance, cross-platform)
Day 3 (Wednesday) | 📌 Backlog Creation: Identify User Stories for each module (Visits, Timesheets, AI, Reporting, Notifications, etc.) | ✅ Initial Product Backlog
📌 Prioritize backlog
Day 4 (Thursday) | 📌 UML Diagrams: Start working on General Use Case Diagram | ✅ Use Case Diagram
| 📌 Define Development Environment: Choose tools & tech stack (React, Node.js, PostgreSQL, Flutter, TensorFlow.js, etc.) | ✅ Tech Stack Defined
Day 5 (Friday) | 📌 System Architecture Design: Define MVC architecture | ✅ Initial Class Diagram and DFD
📌 UML: Start Class Diagram and Data Flow Diagram (DFD)
Weekend (Optional) | 📌 Catch up on UML diagrams if needed | ✅ Refined UML
Day 6 (Monday) | 📌 Finalize Backlog: Assign Story Points & Complexity | ✅ Sprint Release Plan
📌 Release Planning: Define Sprint Goals for next 7 sprints
Day 7 (Tuesday) | 📌 Setup GitHub Repo: Create branches for Frontend, Backend, Mobile, AI | ✅ GitHub Repo & Environment Setup
📌 Setup Project Environments: Install necessary tools
Day 8 (Wednesday) | 📌 Finalize System Architecture & Packages | ✅ Package Diagram
📌 Create Package Diagram (optional)
Day 9 (Thursday) | 📌 Refine Diagrams: Update Class & Sequence Diagrams | ✅ Finalized Class & Sequence Diagrams
Day 10 (Friday) | 📌 Sprint 1 Review: Ensure all planning tasks are completed | ✅ Ready for Sprint 2
📌 Sprint 2: Authentication & User Management (Week 3-4)
Goal: Develop JWT authentication, role management, and basic UI for login
Day | Tasks | Deliverables
Day 11 (Monday) | 📌 Create Database Schema for Users & Roles (PostgreSQL) | ✅ User & Role Schema
📌 Implement Role-Based Access Control (RBAC)
Day 12 (Tuesday) | 📌 Backend Authentication API: Login, Registration, Logout (JWT) | ✅ Auth API Completed
Day 13 (Wednesday) | 📌 Unit Testing: Write test cases for authentication (Jest, Mocha) | ✅ Auth API Unit Tests
Day 14 (Thursday) | 📌 Frontend Login Page: Basic UI with React.js | ✅ Login Page UI
Day 15 (Friday) | 📌 Flutter Mobile Login Page | ✅ Flutter Login UI
Weekend (Optional) | 📌 Debug Authentication Issues | ✅ Fixes Applied
Day 16 (Monday) | 📌 Connect Frontend & Backend (Auth API Integration) | ✅ Working Login System
Day 17 (Tuesday) | 📌 Admin Panel UI (User Management) | ✅ Admin Panel UI
Day 18 (Wednesday) | 📌 Security Hardening: Password hashing (bcrypt) & OWASP compliance | ✅ Secured Authentication
Day 19 (Thursday) | 📌 Sprint 2 Review & Fix Bugs | ✅ Ready for Sprint 3
📌 Sprint 3: Visit Logging & Timesheet Management (Week 5-6)
Goal: Implement visit logging & timesheet functionalities
Day | Tasks | Deliverables
Day 20 (Monday) | 📌 Database Schema for Visits & Timesheets | ✅ Database Schema
Day 21 (Tuesday) | 📌 Backend API (Visit Logging CRUD) | ✅ Visit API Ready
Day 22 (Wednesday) | 📌 Backend API (Timesheet CRUD) | ✅ Timesheet API Ready
Day 23 (Thursday) | 📌 Frontend Visit Logging Page | ✅ Web UI Visit Page
Day 24 (Friday) | 📌 Flutter Visit Logging Page | ✅ Mobile UI Visit Page
Weekend (Optional) | 📌 Optimize APIs | ✅ Optimized API
Day 25 (Monday) | 📌 Real-time Updates with Socket.IO | ✅ Real-Time Data Sync
Day 26 (Tuesday) | 📌 Testing & Debugging Visit Management | ✅ Working Visit Module
Day 27 (Wednesday) | 📌 Sprint 3 Review & Fix Bugs | ✅ Ready for Sprint 4
📌 Sprint 4: AI Integration - Phi-4 Anomaly Detection (Week 7-8)
Goal: Integrate Phi-4 AI model for anomaly detection in timesheets
Day | Tasks | Deliverables
Day 28 (Monday) | 📌 Understand Phi-4 API & Prepare Dataset | ✅ Dataset Ready
Day 29 (Tuesday) | 📌 Integrate AI with Backend (Node.js API) | ✅ AI API Ready
Day 30 (Wednesday) | 📌 Test AI Model Predictions | ✅ AI Anomaly Testing
Day 31 (Thursday) | 📌 Frontend AI Alerts UI | ✅ AI Alerts UI
Day 32 (Friday) | 📌 Sprint 4 Review & Fix Bugs | ✅ Ready for Sprint 5
📌 Sprint 5: Reporting & Notifications (Week 9-10)
Goal: Develop report generation, KPI dashboards, real-time notifications, and alerts
Day | Tasks | Deliverables
Day 33 (Monday) | 📌 Define Reporting Features: Identify key KPIs & report types (PDF, Excel) | ✅ Reporting Features List
📌 Database Schema: Ensure all required data for reports exists
Day 34 (Tuesday) | 📌 Backend API (Reports): Develop report generation endpoints | ✅ Report API Ready
Day 35 (Wednesday) | 📌 Frontend Report UI: Develop dashboard for reports (React.js) | ✅ Report Dashboard UI
Day 36 (Thursday) | 📌 Mobile Report UI: Develop reports section in Flutter app | ✅ Mobile Reports Page
Day 37 (Friday) | 📌 Test Report Generation (Accuracy, Performance) | ✅ Reports Fully Functional
Weekend (Optional) | 📌 Refine report UI & fix minor bugs | ✅ Improved Reports
Day 38 (Monday) | 📌 Implement Real-Time Notifications (Socket.IO) | ✅ Web Real-Time Notifications
Day 39 (Tuesday) | 📌 Push Notifications (Mobile - FCM) | ✅ Mobile Push Notifications
Day 40 (Wednesday) | 📌 Notification Settings (User Preferences UI) | ✅ Notification Settings UI
Day 41 (Thursday) | 📌 Test Notifications (Speed & Reliability) | ✅ Fully Functional Notifications
Day 42 (Friday) | 📌 Sprint 5 Review & Fix Bugs | ✅ Ready for Sprint 6
📌 Sprint 6: Performance & Security Optimization (Week 11-12)
Goal: Optimize database queries, API speed, security enforcement, and penetration testing
Day | Tasks | Deliverables
Day 43 (Monday) | 📌 Analyze Performance Bottlenecks (Database, API, Frontend) | ✅ Performance Report
Day 44 (Tuesday) | 📌 Optimize Database Queries: Indexing, caching, reducing joins | ✅ Optimized Database
Day 45 (Wednesday) | 📌 Optimize API Calls: Minimize payload, improve response times | ✅ Faster API Calls
Day 46 (Thursday) | 📌 Optimize Frontend Rendering (Lazy loading, caching, paginated lists) | ✅ Faster Frontend Performance
Day 47 (Friday) | 📌 Test Performance Improvements (Load Testing) | ✅ Load Testing Report
Weekend (Optional) | 📌 Fine-tune API performance | ✅ More Optimizations
Day 48 (Monday) | 📌 Implement Security Enhancements: Harden APIs (JWT expiry, role-based checks) | ✅ Secured API
Day 49 (Tuesday) | 📌 Encrypt Sensitive Data (Database, Local Storage, Sessions) | ✅ Encrypted Data Storage
Day 50 (Wednesday) | 📌 Penetration Testing (SQL Injection, XSS, OWASP Security Tests) | ✅ Security Test Report
Day 51 (Thursday) | 📌 Fix Security Issues from Penetration Testing | ✅ Security Bugs Fixed
Day 52 (Friday) | 📌 Sprint 6 Review & Final Fixes | ✅ Ready for Sprint 7
📌 Sprint 7: Full System Testing & Documentation (Week 13-14)
Goal: Conduct full system testing, bug fixing, and finalize technical/user documentation
Day | Tasks | Deliverables
Day 53 (Monday) | 📌 Plan Full Testing Strategy: Define test cases (Unit, Integration, UI, AI, Performance) | ✅ Test Strategy Document
Day 54 (Tuesday) | 📌 Run Unit Tests (Jest, Mocha) & Fix Failing Tests | ✅ Unit Tests Passed
Day 55 (Wednesday) | 📌 Run API Integration Tests (Postman, Cypress) | ✅ API Tests Completed
Day 56 (Thursday) | 📌 Run UI Tests (Manual & Automated - Cypress) | ✅ UI Testing Report
Day 57 (Friday) | 📌 Test AI Model Accuracy (False Positives/Negatives Analysis) | ✅ AI Validation Report
Weekend (Optional) | 📌 Fix any remaining testing issues | ✅ Bug Fixes
Day 58 (Monday) | 📌 Start Writing Technical Documentation (API Docs, UML, Security Guide) | ✅ API Documentation Started
Day 59 (Tuesday) | 📌 Write System Architecture Documentation (UML, Diagrams, Data Flow) | ✅ System Docs Ready
Day 60 (Wednesday) | 📌 Write User Manuals (Step-by-step guides, screenshots) | ✅ User Guide Ready
Day 61 (Thursday) | 📌 Compile Final Documentation for Deployment & Review | ✅ Documentation Pack Completed
Day 62 (Friday) | 📌 Sprint 7 Review & Fix Final Bugs | ✅ Ready for Sprint 8
📌 Sprint 8: Deployment & Finalization (Week 15-16)
Goal: Deploy project, finalize report, and prepare for the final defense.
Day | Tasks | Deliverables
Day 63 (Monday) | 📌 Setup Production Server (Backend & Database on Cloud/Local Server) | ✅ Backend Deployed
Day 64 (Tuesday) | 📌 Deploy Web App (React.js) to Cloud (e.g., AWS, Vercel) | ✅ Web App Deployed
Day 65 (Wednesday) | 📌 Deploy Mobile App to Google Play & Apple App Store | ✅ Mobile App Deployed
Day 66 (Thursday) | 📌 Run Post-Deployment Tests (API, Database, UI, AI) | ✅ Post-Deployment Report
Day 67 (Friday) | 📌 Monitor Performance in Production Environment | ✅ Live Performance Report
Weekend (Optional) | 📌 Prepare for project defense | ✅ Ready for Defense
Day 68 (Monday) | 📌 Create Final Presentation Slides (Clear, Simple, Focused on Key Features) | ✅ Presentation Ready
Day 69 (Tuesday) | 📌 Write Project Report (Executive Summary, Problem, Solution, Technical Details, Future Work) | ✅ Report Draft Ready
Day 70 (Wednesday) | 📌 Review & Proofread Report | ✅ Final Report Completed
Day 71 (Thursday) | 📌 Practice Project Defense (Mock Q&A, Fix Issues) | ✅ Ready for Defense
Day 72 (Friday) | 📌 Final Project Submission & Defense Presentation | ✅ Final PFE Submitted & Presented 🎉